NSEI Sablefish MSE — Stakeholder Update

August 2026

Status

Analytical work on the NSEI sablefish Management Strategy Evaluation (MSE) is progressing well. Two major milestones have been completed.

Operating model conditioning is complete. The operating model has been conditioned on historical NSEI sablefish data and includes three scenarios representing plausible future states of the stock: a Baseline OM, a productivity regime shift OM, and a stock crash OM. These three OMs bracket the key uncertainties we want management to be robust to.

Preliminary harvest control rules (HCRs) have been evaluated. A grid of candidate HCRs has been screened across all three operating models, providing an initial picture of how different management approaches perform under each scenario. These results will serve as the basis for discussion with ADF&G and stakeholders.

Next Steps

To move forward, we need to convene a meeting with ADF&G and stakeholders to review the operating model scenarios and agree on the final set of HCR candidates to carry into the full MSE analysis. The meeting should address:

- Review and sign-off on the three operating model scenarios

- Discussion of performance metrics and stakeholder priorities (e.g., yield, stability, risk tolerance)

- Selection of HCR candidates to evaluate in detail